## Project Plan
Plan start (Monday) | 2026-10-05 |  | Timeline (weeks) | 78 | Project duration |  |  | 18 months
Legend: | Summary | Task | Milestone
ID | Task name | Type | Start | Finish | Duration (days) | Predecessors | Resource names | Work (hours) | Milestone
1 | CBS Implementation | Summary | 2026-10-05 | 2028-04-05 | 548 |  |  | 12443 (total) | No
2 | I. Project Planning & Initiation | Summary | 2026-10-05 | 2026-11-13 | 39 |  |  | 500 | No
3 | 1. Mobilisation, governance setup (committees, roles, escalation) | Task | [6 empty] | No
4 | 2. Project Management Plan (IPMP) & subsidiary management plans (Quality, Risk, Change, Communication) | Task | [6 empty] | No
5 | 3. Detailed project plan / Gantt & Phase Plan(s) baseline | Task | [6 empty] | No
6 | 4. Project Library setup & document control/versioning | Task | [6 empty] | No
7 | 5. Kick-off meeting package (agenda, minutes, actions log) | Task | [6 empty] | No
8 | II. Analysis & Design | Summary | 2026-11-14 | 2027-03-14 | 120 |  |  | 2000 | No
9 | 1. Detailed Software Requirements Specification (SRS) / Requirements baseline | Task | 2026-11-14 | 2026-12-20 | 36 |  |  | 350 | No
10 | 2. Acceptance criteria definition (per deliverable/phase/module) | Task | 2026-12-01 | 2027-01-05 | 35 |  |  | 90 | No
11 | 3. Conceptual data model | Task | 2026-12-01 | 2027-01-20 | 50 |  |  | 220 | No
12 | 4. Conceptual solution architecture & infrastructure diagrams | Task | 2026-11-25 | 2027-01-15 | 51 |  |  | 240 | No
13 | 5. Gap analysis and solution design for identified gaps | Task | 2026-12-20 | 2027-02-05 | 47 |  |  | 300 | No
14 | 6. Solution configuration approach (parameters/settings catalogue) | Task | 2027-01-10 | 2027-02-15 | 36 |  |  | 120 | No
15 | 7. Integration specifications (interfaces catalogue, mappings) | Task | 2027-01-15 | 2027-02-28 | 44 |  |  | 220 | No
16 | 8. Data mapping & conversion rules (migration design) | Task | 2027-01-20 | 2027-03-05 | 44 |  |  | 240 | No
17 | 9. Reporting catalogue and definition of 75+ customised reports (Lot 1) | Task | 2027-02-01 | 2027-03-10 | 37 |  |  | 180 | No
18 | 10. A&D phase provisional acceptance package | Milestone | 2027-03-14 | 2027-03-14 | 0 |  |  | 40 | Yes
19 | III. Construction / Build | Summary | 2027-01-15 | 2027-12-15 | 334 |  |  | 3800 | No
20 | 1. Environments prepared (DEV/TEST/TRAIN) and baseline configuration | Task | [6 empty] | No
21 | Workstream 1. Core Banking & Payments (payments/funds transfers processing, payment-related messaging and connectivity, cash operations) | Summary | [6 empty] | No
22 | - Configure/customise and implement scope | Task | [6 empty] | No
23 | - Demonstrations / iterative feedback incorporation | Task | [6 empty] | No
24 | - Updated documentation and self-assessment evidence | Task | [6 empty] | No
25 | Workstream 2. Remote Banking Services (Remote Banking component, secure messaging and document exchange, electronic signatures and multi-level authorization) | Summary | [6 empty] | No
26 | - Configure/customise and implement scope | Task | [6 empty] | No
27 | - Demonstrations / iterative feedback incorporation | Task | [6 empty] | No
28 | - Updated documentation and self-assessment evidence | Task | [6 empty] | No
29 | Workstream 3. Loans & Treasury (Treasury operations (money, FX, financial market), REPO instruments, securities operations, deposits, loans, IMF-related operations, required reserves operations) | Summary | [6 empty] | No
30 | - Configure/customise and implement scope | Task | [6 empty] | No
31 | - Demonstrations / iterative feedback incorporation | Task | [6 empty] | No
32 | - Updated documentation and self-assessment evidence | Task | [6 empty] | No
33 | Workstream 4. Reporting (reporting needs analysis + report catalogue, minimum 75 customised reports for Lot 1) | Summary | [6 empty] | No
34 | - Configure/customise and implement scope | Task | [6 empty] | No
35 | - Demonstrations / iterative feedback incorporation | Task | [6 empty] | No
36 | - Updated documentation and self-assessment evidence | Task | [6 empty] | No
37 | Workstream 5. Integration (CBS ↔ ERP interoperability and integration with existing NBM systems, third-party/external integrations) | Summary | [6 empty] | No
38 | - Configure/customise and implement scope | Task | [6 empty] | No
39 | - Demonstrations / iterative feedback incorporation | Task | [6 empty] | No
40 | - Updated documentation and self-assessment evidence | Task | [6 empty] | No
41 | Workstream 6. Data migration (transition from current systems to the future solution) | Summary | [6 empty] | No
42 | - Configure/customise and implement scope | Task | [6 empty] | No
43 | - Demonstrations / iterative feedback incorporation | Task | [6 empty] | No
44 | - Updated documentation and self-assessment evidence | Task | [6 empty] | No
45 | Workstream 7. Non-functional & Security (availability, resilience and continuity targets, performance targets, security controls, backup/recovery and operational monitoring) | Summary | [6 empty] | No
46 | - Configure/customise and implement scope | Task | [6 empty] | No
47 | - Demonstrations / iterative feedback incorporation | Task | [6 empty] | No
48 | - Updated documentation and self-assessment evidence | Task | [6 empty] | No
49 | 2. Construction phase provisional acceptance package | Milestone | [6 empty] | Yes
50 | IV. Testing | Summary | 2027-03-15 | 2028-01-15 | 306 |  |  | 2200 | No
51 | 1. Test strategy & High-Level Test Plan (HLTP) | Task | [6 empty] | No
52 | 2. Detailed test specifications/scripts & test data preparation | Task | [6 empty] | No
53 | 3. Supplier-side testing execution & Supplier Test Report | Task | [6 empty] | No
54 | 4. Beneficiary UAT preparation & support | Task | [6 empty] | No
55 | 5. Defect management, retesting & regression testing | Task | [6 empty] | No
56 | 6. Testing phase provisional acceptance package | Milestone | [6 empty] | Yes
57 | V. Training | Summary | 2027-11-01 | 2028-01-30 | 90 |  |  | 350 | No
58 | 1. Training strategy and training plan/programme | Task | [6 empty] | No
59 | 2. Training materials (end users, admins, technical) | Task | [6 empty] | No
60 | 3. Training sessions execution | Task | [6 empty] | No
61 | 4. Knowledge tests & satisfaction feedback | Task | [6 empty] | No
62 | 5. Training acceptance evidence | Milestone | [6 empty] | Yes
63 | VI. Preparing for Go-Live | Summary | 2028-02-10 | 2028-03-15 | 34 |  |  | 500 | No
64 | 1. Cutover & Go-live plan (incl. rollback) | Task | [6 empty] | No
65 | 2. Readiness assessment (IT and business readiness) | Task | [6 empty] | No
66 | 3. Defect remediation plan (focus on residual Sev3/4) and closure tracking | Task | [6 empty] | No
67 | 4. Go-live self-assessment report (requirements coverage) | Task | [6 empty] | No
68 | 5. Release acceptance decision | Milestone | [6 empty] | Yes
69 | VII. Go-Live | Summary | 2028-03-15 | 2028-04-05 | 21 |  |  | 450 | No
70 | 1. Production deployment & verification | Task | [6 empty] | No
71 | 2. Go-live support start | Task | [6 empty] | No
72 | 3. Go-live acceptance | Milestone | [6 empty] | Yes
73 | VIII. Experimental Exploitation (Soak) | Summary | 2028-04-05 | 2028-07-05 | 91 |  |  | 650 | No
74 | 1. On-site support, monitoring & help desk | Task | [6 empty] | No
75 | 2. Weekly remediation status reporting | Task | [6 empty] | No
76 | 3. End-of-day / end-of-month processing validation | Task | [6 empty] | No
77 | 4. Soak phase acceptance | Milestone | [6 empty] | Yes
78 | IX. Final Acceptance | Summary | 2028-07-05 | 2028-07-25 | 20 |  |  | 120 | No
79 | 1. Final acceptance criteria review and evidence compilation | Task | [6 empty] | No
80 | 2. Final acceptance act signed | Milestone | [6 empty] | Yes
81 | 3. Warranty/guarantee period start | Milestone | [6 empty] | Yes
82 | X. Solution Documentation | Summary | 2027-05-01 | 2028-04-01 | 336 |  |  | 300 | No
83 | 1. User guides & work instructions | Task | [6 empty] | No
84 | 2. Administrator documentation | Task | [6 empty] | No
85 | 3. Installation and configuration guides | Task | [6 empty] | No
86 | 4. Backup & recovery procedures | Task | [6 empty] | No
87 | 5. Archiving & search procedures | Task | [6 empty] | No
88 | 6. Security documentation (access control, audit, monitoring) | Task | [6 empty] | No
89 | 7. Commented source code and technical documentation (if applicable) | Task | [6 empty] | No
90 | 8. Training support materials | Task | [6 empty] | No
91 | XI. Solution Integration (CBS–ERP–3rd parties) | Summary | 2027-08-15 | 2027-12-15 | 122 |  |  | 1573 | No
92 | 1. Integration plan developed and approved | Task | [6 empty] | No
93 | 2. Interfaces developed and documented | Task | [6 empty] | No
94 | 3. Interoperability test plan and scenarios | Task | [6 empty] | No
95 | 4. Interoperability testing results | Task | [6 empty] | No
96 | 5. Interoperability acceptance act signed | Milestone | [6 empty] | Yes