## 1 Change request information
Change request summary
Work Stream: | Core Banking & Payments
Impacted area:
Change description: | [Describe the change here]
Change justification: | [Why is this change required? How urgent is it? Include the impact of NOT implementing the change]
Alternatives/comments: | [Any alternatives to the change required and any other relevant comments]

## 2 Supporting analysis
Impact assessment
Impact assessment date: | [Enter date impact assessment completed] |  | Assessor/ who evaluated: | [Enter name of assessor/ initiator]
Change impact | <Calculate the cost impact using the table below>
| (A) Approved project baseline | (B) Projected change to baseline |  | Variance (the change from A to B)
Scope (quality): | [Describe] | [Describe]
Schedule (time): | [Describe] | [Describe] |  | [Provide increase or decrease in hours, days or months]
Budget (cost): | EUR [amount] | EUR [amount] |  | (C) Variance: EUR [Amount] (Note: C = A - B)
(D) Variance % [%] Note: D = C/A*100
Deliverables impacted | [Deliverables impacted by the change (at a high-level)]
Resource impact | [How does the change impact on the resource required and when?]
Benefits impact | [How does the change impact on benefits delivery?]
Stakeholders impacted | [Who is impacted by the decision and should be informed?]
Risks associated with accepting this change request | [What are the risks associated with accepting this change?]
Risks associated with NOT accepting this change request | [What are the risks associated with not accepting this change?]
Supporting information: | [Add links here to any supporting information for the request or embed any related documents]

## 1 EXAMPLE_CR information
Change request summary
Work Stream: | Core Banking & Payments
Impacted area: | Schedule/Time
Change description: | Deadline for requirements description needs to be postponed on...
Change justification: | This change is required due to the limitation of currently available information. If change is not confirmed, there is a risk that requirements would be provided in very poor quality and not full scope.
Alternatives/comments: | 1. Include additional resources to Core banking & Payments Work Stream for transactions data requirements gathering. 2. Provide part of requirements on 22nd March of 2027, and other part on 30 March of 2027.

## 2 EXAMPLE_Supporting analysis
Impact assessment
Impact assessment date: | 2026 12 17 |  | Assessor/ who evaluated: | Name Surname
Change impact | <Calculate the cost impact using the table below>
| (A) Approved project baseline | (B) Projected change to baseline |  | Variance (the change from A to B)
Scope (quality): | [Describe] | [Describe] |  | 9 days
Schedule (time): | 22 December (requirements provision deadline) | 31 December (requirements provision) |  | [Provide increase or decrease in hours, days or months]
Budget (cost): | EUR [amount] | EUR [amount] |  | (C) Variance: EUR [Amount] (Note: C = A - B)
(D) Variance % [%] Note: D = C/A*100
Deliverables impacted | Business requirements specificaton.
Resource impact | If needed to do on currently agreed time (20th March), additional resources needs to be assigned for Transactions Data Project implementation. If the deadline can be postponed - no additional resources required.
Benefits impact | If change implemented, the requirements would be provided in better quality, fully reviewed.
Stakeholders impacted | OSC and Supplier. Needed OSC approval and Supplier should be communicated if the change is acceptable.
Risks associated with accepting this change request | 1. Critical milestones defined in the Agreement with Supplier might be impacted. 2. Other Critical Milestones might be impacted
Risks associated with NOT accepting this change request | Poor quality of requirements.
Supporting information: | [Add links here to any supporting information for the request or embed any related documents]

## Customization
Drop down list administration
Instructions: To alter the values in the drop down list re-type over the current text. If you require more values than the number provided select Insert ¦ Cells ¦ Shift cells down in the cell above the text marked N/A.
Work stream | Impact area
Core Banking & Payments | Quality/Scope
Remote Banking Services | Schedule/Time
Loans & Treasury | Budget/Cost
Reporting | Complex
Integration | Other
Data Migration
Programme
Various Work Streams
N/A