## Summary
Varnix SIMSM Tender Cost Model
Procedure ID | ocds-b3wdp1-MD-1779798670296 | Metric | Value | Note
Object | Development of the Information System for Monitoring Medicine Stocks (SIMSM) | Labor subtotal | 2795660 | Role hours x hourly rate
Estimated tender value without VAT, MDL | 2872666.66 | Commercial reserve / rounding | 69340 | Fixed price minus modeled labor
Proposed offer without VAT, MDL | 2865000 | Blended rate, MDL/hour | 515.2878 | Offer price / total hours
VAT rate if applicable | 20% | Budget headroom vs estimated value | 7666.66 | Estimated value - proposed price
VAT amount, MDL | 573000 | Bid guarantee | 57300 | 2% of offer without VAT
Proposed offer including VAT, MDL | 3438000 | Performance guarantee | 143250 | 5% of awarded contract
Bid guarantee 2%, MDL | 57300 | Model date | 23 June 2026 | Draft for Varnix review
Performance guarantee 5%, MDL | 143250
Total estimated hours | 5560

## Cost by Role
Role | Hours | Rate MDL/hour | Cost MDL without VAT | Scope
Project Manager / Team Lead | 520 | 513 | 266760 | Project governance, coordination, acceptance support
Solution Architect / Senior Backend | 300 | 650 | 195000 | Architecture, integrations, senior review
Data Analyst / Data Engineer | 650 | 547 | 355550 | Data model, aggregations, dashboards, alerts
Backend Developer | 1350 | 513 | 692550 | APIs, MPass/MConnect/MNotify/MLog, reporting logic
Frontend Developer / UX | 900 | 479 | 431100 | FrontOffice, manual reporting, admin UI, accessibility
DevOps Engineer | 520 | 599 | 311480 | Kubernetes, Helm, CI/CD, environments
QA / Performance Engineer | 600 | 376 | 225600 | Functional, regression and performance testing
Cybersecurity Engineer | 160 | 684 | 109440 | Threat model, OWASP, authorization/security testing
Technical Writer / Trainer | 260 | 308 | 80080 | Documentation and training materials
Management reserve / bugfix buffer | 300 | 427 | 128100 | Cross-role issue remediation and warranty preparation
Labor subtotal | 5560 |  | 2795660
Commercial reserve / rounding |  |  | 69340 | Fixed price reserve
TOTAL OFFER PRICE WITHOUT VAT | 5560 |  | 2865000

## Phase Plan
Phase | Summary | PM/TL | Architect | Data | Backend | Frontend | DevOps | QA/Perf | Security | Writer/Trainer | Reserve | Total Hours
Weeks 0-4 | Analysis and final architecture | 100 | 100 | 120 | 90 | 60 | 50 | 70 | 30 | 30 | 0 | 650
Weeks 5-12 | Core development and first MVP | 120 | 70 | 190 | 470 | 420 | 150 | 160 | 20 | 40 | 110 | 1750
Weeks 13-18 | Integrations and extended functionality | 130 | 70 | 190 | 510 | 280 | 140 | 150 | 50 | 40 | 40 | 1600
Weeks 19-22 | Registrar integrations, production and performance | 90 | 40 | 90 | 170 | 80 | 130 | 150 | 40 | 50 | 10 | 850
Weeks 23-26 | Security, training, final adjustments and acceptance | 80 | 20 | 60 | 110 | 60 | 50 | 70 | 20 | 100 | 140 | 710
TOTAL |  | 520 | 300 | 650 | 1350 | 900 | 520 | 600 | 160 | 260 | 300 | 5560

## Payment Milestones
Milestone | Deliverable | Timing | Share | Amount without VAT, MDL | Notes
M1 | Architecture and analysis accepted | End of Week 4 | 15% | 429750 | Architecture document, data model, API draft, test plan
M2 | Core platform and MVP accepted | End of Week 12 | 30% | 859500 | Staging MVP, initial APIs, first performance test
M3 | Integrations and extended functionality accepted | End of Week 18 | 25% | 716250 | MPass/MConnect/MNotify integrations, FrontOffice flows
M4 | Production deployment, performance and documentation accepted | End of Week 22 | 20% | 573000 | Production deployment, repeated performance test, final guides
M5 | Security testing, training and final acceptance | End of Week 26 | 10% | 286500 | Security report, training, final acceptance package
TOTAL |  |  | 100% | 2865000

## Assumptions
Area | Assumption / clarification
Client access and decisions | AMDM, AGE, STISC and platform owners provide timely access, decisions, credentials and approvals.
Government platforms | MPass, MConnect, MNotify, MLog and MCloud/KaaS access and support are provided by responsible parties.
Scope baseline | Fixed price covers the tender scope and agreed proposal. Material changes are subject to change control.
Dashboard/alert baseline | At least 10 aggregations, 10 visualizations and 10 alert/notification rules are included.
Registrar systems | Development inside external registrar systems is excluded; Varnix supports SIMSM API integration testing.
Infrastructure | Hardware, paid licenses and non-MCloud costs are excluded unless explicitly accepted.
Security | OWASP-oriented testing is included; independent external audit/certification is excluded unless added.
Documentation languages | Delivery documentation follows tender language requirements; this workbook is English for Varnix review.
Warranty | 12 months warranty/maintenance included after final acceptance; new features are outside warranty.
Pricing source | Cost model is derived from Varnix internal SIMSM effort analysis, not from the attached Indictrans offer.