## Sheet1
Risk Register
Key Risks
Risk ID | Project Phase | Identification date | Date of last revision | Description | Risk responsible | Severity | Probability | Impact | Proposed Resolution | Status
1 | Testing | N/A | N/A | Resource (e.g. Analyst), dedicated to the particular task, which has direct influence on the project timely delivery, took an unexpected absence leave -> project is in a high risk of delay. | Forbis | High | Medium | High | PM to create substitution plan for each resource involved in a project. Also, admin/user guides/manuals to be prepared where possible for a smooth transition of resources. | Open
2 | Design | N/A | N/A | Only one Employee in the company has required skills to deliver on a project task (e.g. design). | Forbis | High | Medium | High | Start knowledge transfer ASAP; ask HR department to open a new vacancy. | Open
3 | Applicable to all phases | N/A | N/A | Risk of new legislation that can constraint the scope or delivery of the project. | NBM | High | Low | Medium | NBM to keep track of any upcoming legislation in the country to take into effect and inform Forbis ASAP. | Open
4 | Analysis | N/A | N/A | The current project schedule baseline is aggressive and considered high risk for completing project work on time. | Forbis | High | Low | High | Carefully monitor work performance and search for opportunities to reduce risk. Worst case scenario - re-work and re-baseline the schedule to be less aggressive. | Open
5 | Design | N/A | N/A | System integration is more complex than estimated. | Forbis | Medium | Medium | High | Early development of integration plan with formal entry requirements for components entering integration. | Open
6 | Applicable to all phases | N/A | N/A | Third party-related risks (e.g. regulatory, compliance). | NBM | High | Low | High | Careful assessment of contractual obligations with the third party in earliest project phases, monitoring of expected deliverables and other risk factors. | Open
7 | Analysis | N/A | N/A | Changes in the requirements that lead to the increase of the project scope. | Forbis/NBM | Medium | Medium | Medium | Drawing-up of a Change Request. | Open
8 | Testing | N/A | N/A | Insufficient planned time for testing. | Forbis/NBM | Medium | Medium | Medium | It is necessary to plan enough time and resources for testing while on the stage of planning; to ensure additional reporting on the results of testing. | Open
N/A - not applicable at this moment, as this risk register lists only the potential future risks.

## Sheet2
Project phases: | Impact: | Probability: | Severity: | Risk status:
Analysis | High | High | Critical | Open
Design | Medium | Medium | High | Closed
Build | Low | Low | Medium
Testing |  |  | Low
Training
Go-live
Documentation
Applicable to all phases