Annex 1 eng

| Stage 2 (will NOT be awarded in the price offers within this auction): B2B promotional activities, which will be contracted financially by wineries separately (NOT by ONVV). |  |  |  |  |
| --- | --- | --- | --- | --- |
| Listings moldovan wines | Service | 1 | Identification and contacting at least 6 agents and retailers to encourage listings wines from 10 wineries. Portfolio per company will consist of 6-8 wines, and negotiations will be made for a maximum number of wines. Wineries and protfoliu will be selected by the NOVW. The agents/retailers will be coordinated in advance with NOVW. Timeline: 10 days from the moment of signing the contract. |  |
| Sampling transportation | Service | 1 | Sampling initiative - offering up to 12 samples to at least 6 agents/retailers with a view to purchasing wines. Two weeks window to make an order, which is consolidated and sent over from Moldova and distributed accordingly. Companies will choose the wines they want to taste and the sampling sending will be organised accordingly. The bidder will be responsible for organizing all logistic process and delivery service costs from Moldova to UK (including all customs and local taxes). Duration: 5 days |  |
| Wine tasting in London | Service | 1 | London tasting - informal tasting of all wines provided from the 10 wineries (without winery representatives)) aimed at agents/retailers/influencers (could be Winerist offices: over two days). Contacting at least 10 agents/retailers/influencers, identifying the location, logistics for the event. Will be provided by the bidder. Duration: 7 days |  |
| Online webinar | Service | 1 | Organizing and development of the webinar and panel tasting on the future for Moldova in the UK. Duration of the webinar 2 hours. In costs will be included: delivery of wines to participant. The group of participants will be consisted from 2 from Moldova, retail, buyers, agents. Only participants from UK, registering and posting on our platform for UK market. Tha date of webinar will be agreed with the NOVW. Duration: 1 day |  |