## Offer
# | Description of Activity/Item | Effort(M/H) | COST(MDL) | Devel, Days | Rate, MDL/D | Rate, MDL/H
1 | Analysis | 272 | 251804.544 | 42 days | 7406.016 | 925.752
| Existing requirements analysis | 14 | 12960.528 | 2 days | 7406.016 | 925.752
| Entity base analysis/system actors | 14 | 12960.528 | 2 days | 7406.016 | 925.752
| Mind-map creation | 14 | 12960.528 | 2 days | 7406.016 | 925.752
| Business flow details | 36 | 33327.072 | 6 days | 7406.016 | 925.752
| Functional details | 48 | 44436.096 | 7 days | 7406.016 | 925.752
| Non-functional details | 14 | 12960.528 | 2 days | 7406.016 | 925.752
| Detailed business requirements document | 71 | 65728.392 | 11 days | 7406.016 | 925.752
| Client meetings | 25 | 23143.8 | 4 days | 7406.016 | 925.752
| Feedback | 36 | 33327.072 | 6 days | 7406.016 | 925.752
2 | Design | 325 | 300869.4 | 21 days | 7406.016 | 925.752
| UI Kit | 21 | 19440.792 | 3 days | 7406.016 | 925.752
| Wire frames | 51 | 47213.352 | 7 days | 7406.016 | 925.752
| Management Recrutare | 21 | 19440.792 | 3 days | 7406.016 | 925.752
| Angajare și Administrare Personal | 21 | 19440.792 | 3 days | 7406.016 | 925.752
| Structura Organizatorică | 21 | 19440.792 | 3 days | 7406.016 | 925.752
| Evidența Timpului de Muncă | 21 | 19440.792 | 3 days | 7406.016 | 925.752
| Gestionarea Concediilor | 21 | 19440.792 | 3 days | 7406.016 | 925.752
| Gestionarea Beneficiilor | 21 | 19440.792 | 3 days | 7406.016 | 925.752
| Documente și Fluxuri de Aprobări | 21 | 19440.792 | 3 days | 7406.016 | 925.752
| Raportare și Analiză | 21 | 19440.792 | 3 days | 7406.016 | 925.752
| Notificări și Alerte | 21 | 19440.792 | 3 days | 7406.016 | 925.752
| Configurare și Personalizare | 11 | 10183.272 | 2 days | 7406.016 | 925.752
| Responsive design | 53 | 49064.856 | 7 days | 7406.016 | 925.752
3 | Technical document | 65 | 60173.88 | 9 days | 7406.016 | 925.752
| Description of the technology and methods of realization | 7 | 6480.264 | 1.0 days | 7406.016 | 925.752
| Description of the software system architecture and its elements (Low level design) | 7 | 6480.264 | 1.0 days | 7406.016 | 925.752
| Description of the interaction model of the elements | 7 | 6480.264 | 1.0 days | 7406.016 | 925.752
| Description of data structures, classes, interfaces | 7 | 6480.264 | 1.0 days | 7406.016 | 925.752
| Description of information processing algorithms | 7 | 6480.264 | 1.0 days | 7406.016 | 925.752
| Description of user interface structures | 7 | 6480.264 | 1.0 days | 7406.016 | 925.752
| The technical document | 23 | 21292.296 | 3.3 days | 7406.016 | 925.752
4 | Infrastructure | 279 | 258284.808 | 35 days | 7406.016 | 925.752
| Infrastructure | 253 | 234215.256 | 32 days | 7406.016 | 925.752
| CI/CD | 26 | 24069.552 | 3 days | 7406.016 | 925.752
5 | Development | 2434 | 2253280.368 | 151 days | 7406.016 | 925.752
| Architectura | 252 | 233289.504 | 16 days | 7406.016 | 925.752
| Configurare DMS | 69 | 63876.888 | 4 days | 7406.016 | 925.752
| Gestionarea angajatilor | 485 | 448989.72 | 30 days | 7406.016 | 925.752
| Posturi vacante | 164 | 151823.328 | 10 days | 7406.016 | 925.752
| Formulare prestabilite | 73 | 67579.896 | 5 days | 7406.016 | 925.752
| Fluxuri de lucru | 95 | 87946.44 | 6 days | 7406.016 | 925.752
| Salarizare | 133 | 123125.016 | 8 days | 7406.016 | 925.752
| Archivarea informatiei | 50 | 46287.6 | 3 days | 7406.016 | 925.752
| Organigrama institutiei | 64 | 59248.128 | 4 days | 7406.016 | 925.752
| Notificari | 68 | 62951.136 | 4 days | 7406.016 | 925.752
| Raportari | 175 | 162006.6 | 11 days | 7406.016 | 925.752
| Integrari / migrari | 806 | 746156.112 | 50 days | 7406.016 | 925.752
8 | Testing | 360 | 333270.72 | 51 days | 7406.016 | 925.752
9 | PM hours | 596 | 551748.192 | 99 days | 7406.016 | 925.752
10 | Training | 102 | 94426.704 | 17 days | 7406 | 925.752
11 | Maintenance + post garantie + 300 ore + 100 ore | 940 | 870206.88 | 157 days | 7406 | 925.752
| TOTAL | 5373 | 4974065.496 | TVA 0% | 7406 | 925.75

## Gantt
 | time axis 2025-01-02 to 2025-12-15
Type | Task list | Start Date | End Date | # days | 2025-01-02: Week 1; 2025-01-07: Week 2; 2025-01-14: Week 3; 2025-01-21: Week 4; 2025-01-28: Week 5; 2025-02-04: Week 6; 2025-02-11: Week 7; 2025-02-18: Week 8; 2025-02-25: Week 9; 2025-03-04: Week 10; 2025-03-11: Week 11; 2025-03-18: Week 12; 2025-03-25: Week 13; 2025-04-01: Week 14; 2025-04-08: Week 15; 2025-04-15: Week 16; 2025-04-22: Week 2; 2025-04-29: Week 3; 2025-05-06: Week 4; 2025-05-13: Week 5; 2025-05-20: Week 6; 2025-05-27: Week 7; 2025-06-03: Week 8; 2025-06-10: Week 9; 2025-06-17: Week 10; 2025-06-24: Week 11; 2025-07-01: Week 12; 2025-07-08: Week 13; 2025-07-15: Week 14; 2025-07-22: Week 15; 2025-07-29: Week 16; 2025-08-05: Week 2; 2025-08-12: Week 3; 2025-08-19: Week 4; 2025-08-26: Week 5; 2025-09-02: Week 6; 2025-09-09: Week 7; 2025-09-16: Week 8; 2025-09-23: Week 9; 2025-09-30: Week 10; 2025-10-07: Week 11; 2025-10-14: Week 12; 2025-10-21: Week 13; 2025-10-28: Week 14; 2025-11-04: Week 15; 2025-11-11: Week 16; 2025-11-18: Week 17; 2025-11-25: Week 18; 2025-12-02: Week 19; 2025-12-09: Week 20
Analysis | Existing requirements analysis | 2025-01-02 | 2025-01-06 | 2
| Entity base analysis/system actors | 2025-01-06 | 2025-01-08 | 2
| Mind-map creation | 2025-01-08 | 2025-01-10 | 2
| Business flow details | 2025-01-10 | 2025-01-20 | 6
| Functional details | 2025-01-20 | 2025-01-29 | 7
| Non-functional details | 2025-01-29 | 2025-01-31 | 2
| Detailed business requirements document | 2025-01-31 | 2025-02-17 | 11
| Client meetings | 2025-02-17 | 2025-02-21 | 4
| Feedback | 2025-02-21 | 2025-03-03 | 6
Design | Design additional modules | 2025-03-03 | 2025-04-25 | 39
| Responsive design | 2025-04-25 | 2025-05-06 | 7
Technical Documentation | Technical Documentation | 2025-03-11 | 2025-03-25 | 10
Infrastructure | Infrastructure | 2025-03-25 | 2025-05-08 | 32
| CI/CD | 2025-05-08 | 2025-05-13 | 3
Development | Architectura | 2025-05-13 | 2025-06-04 | 16
| Configurare DMS | 2025-06-04 | 2025-06-10 | 4
| Gestionarea angajatilor | 2025-06-10 | 2025-07-22 | 30
| Posturi vacante | 2025-07-22 | 2025-08-05 | 10
| Formulare prestabilite | 2025-08-05 | 2025-08-12 | 5
| Fluxuri de lucru | 2025-08-12 | 2025-08-20 | 6
| Salarizare | 2025-08-20 | 2025-09-01 | 8
| Archivarea informatiei | 2025-09-01 | 2025-09-04 | 3
| Organigrama institutiei | 2025-09-04 | 2025-09-10 | 4
| Notificari | 2025-09-10 | 2025-09-16 | 4
| Raportari | 2025-09-16 | 2025-10-01 | 11
| Integrari / migrari | 2025-10-01 | 2025-12-10 | 50
Testing | Testing | 2025-09-29 | 2025-12-09 | 51
Formulas:
End Date = WORKDAY([Start Date],F4)
Start Date = [End Date, row above]
Start Date = [End Date, row above]-56