ANNEX II: TERMS OF REFERENCE

1.	BACKGROUND INFORMATION	2

1.1.	Partner country	2

1.2.	Contracting Authority	2

1.3.	Country background	2

1.4.	Current situation in the sector	2

1.5.	Related programmes and other donor activities	2

2.	OBJECTIVE, PURPOSE & EXPECTED RESULTS	2

2.1.	Overall objective	2

2.2.	Purpose	3

2.3.	Results to be achieved by the Contractor	3

3.	ASSUMPTIONS & RISKS	3

3.1.	Assumptions underlying the project	3

3.2.	Risks	3

4.	SCOPE OF THE WORK	3

4.1.	General	3

4.2.	Specific work	3

4.3.	Project management	4

5.	LOGISTICS AND TIMING	5

5.1.	Location	5

5.2.	Start date & period of implementation	5

6.	REQUIREMENTS	5

6.1.	Personnel 	5

6.2.	Office accommodation	8

6.3.	Facilities to be provided by the Contractor	8

6.4.	Equipment	8

6.5.	Incidental expenditure	8

6.6.	Lump sums	9

6.7.	Expenditure verification	10

7.	REPORTS	10

7.1.	Reporting requirements	10

7.2.	Submission & approval of reports	11

8.	MONITORING AND EVALUATION	11

8.1.	Definition of indicators	11

8.2.	Special requirements	11

# BACKGROUND INFORMATION

## Partner country

Republic of Moldova

## Contracting authority

Public Institution "Technical University of Moldova” (TUM)

## Country background

Moldova is an active participant in the Cross Border and Transnational Programs for more than 20 years, having proven its high interest and responsibility for the entrusted funds of the European Union.

The on-going Joint Operational Program Romania–Republic of Moldova 2014–2020, approved by the European Commission Decision C (2015) 9155/ 17.12.2015-Ref.Ares (2015)5993060 - 22/12/2015, is the result of a joint effort of the relevant actors from Romania and Republic of Moldova. Conscious of the important role of universities in achieving the objectives of the Bologna Process, which caused significant changes on the priorities and mission of universities, Technical University of Moldova proposes raising the value of the national engineering education through: the quality of education as a determinant of the competitiveness of local human potential; development of scientific and technical research as an indispensable component in professional engineering training; encouraging mobility of students and teachers; promoting access and integration of graduates in the local labor market, etc. The Technical University of Moldova supports and contributes to regional development through research and educational projects implemented and in progress. In the Joint Operational Program Romania-Republic of Moldova 2014–2020 TUM has 6 ongoing projects, one of them being the Cross-Border Regional Hub of Competences for the Automotive Industry.

## Current situation in the sector

The Project’ work is organized in accordance with the activities assigned through the Work Packages:

GA 1. Project Management

GA 2. Information and Communication plan

- GA 3. Increasing the quality of the academic educational programs

By implementing the above mentioned activities the Contractor will actively contribute to the:

- Planning and develop the joint educational and research strategy in the field of automotive engineering, based on a detailed SWOT analysis of the cross-border area sector;

- Developing a new high-quality interdisciplinary study programme at master level, in the field of automotive engineering – the “Hybrid and Electrical Vehicles” master programme;

- A joint process of improving the curricular content for new or existing disciplines with applicative component related to the automotive engineering sector, as identified in the joint educational and research strategy, using the input about the areas that are representative of automotive-specific subjects and that are perceived by the local private sector to be lacking in graduates from traditional engineering programs;

- Commonly developing the capacity of their academic staff to acquire applied knowledge in curriculum design, project based-learning, new forms of peer and group assessments, regional networking, and teaching using the new technologies;

- Organising a series of 5 webinars, involving students and academic staff from the cross-border area academic consortium members, and hosting invited speakers from regional automotive industry leaders and from the international sector;

- Organising the Automotive Engineering International Summer School (AEISS), involving students from all the three partners;

- Upgrading of 6 laboratories with modern didactic equipment, serving a number of 33 automotive engineering related disciplines, in all the three technical universities forming the partnership.

## Related programmes and other donor activities

The Project has not been developed in isolation, but it is closely related to a wide range of strategies currently operating at EU, national, regional and local levels inside the Programme area. They were taken into account and complement the Project.

# OBJECTIVES & EXPECTED OUTPUTS

## Overall objective

The overall objective of the project of which this contract will be a part is as follows:

“To foster the improvement of the existing cooperation between three cross-border area universities and to transform it into coordinated collaboration, aiming to increase the partners’ institutional capacity to build a labor force linked to the latest requirements of the automotive engineering sector, leading to an increase in the degree of tertiary education students from both sides of the border, equipped with the labor market relevant skills, in order to ensure the improvement of the graduates’ employment rate and to meet regional companies increasing needs”.

## 2.2   Specific objective(s)

The specific objective of this contract is as follows:

To increase the degree of promoting the culture of innovation and entrepreneurship among the students of the three universities from both sides of the border, as well as enabling them to get acquainted with the latest automotive innovation topics, by the means of a joint summer school programme, aiming to equip the students with appropriate, labour market relevant competences, allowing them to acquire the breadth and depth of skills they need.

## Expected outputs to be achieved by the contractor

The expected outputs of this contract are as follows:

- Output 1: Organizing a 7-day summer school for at least 30 people;

- Output 1: Organizing webinars for training, development and administration of online courses on the Moodle platform lasting 2 days for at least 15 people

# ASSUMPTIONS & RISKS

## Assumptions underlying the project

-	It is assumed that a positive perception of the communities living in the area exists in what concerns the Project and the benefits it brings.

-	Confidence in institutions/ organizations managing the Project, and a good reputation as well, are expected to create a favourable environment for the Project developments in the target area.

-	It is assumed that the Contractor will be fully supported in undertaking its activities by the regional / local actors / stakeholders.

## Risks

-	Major delays in Project’s implementation impact directly on the results foreseen to be achieved

# SCOPE OF THE WORK

## General

### Project description

In order to accomplish the tasks assigned to the Contracting Authority within the “Automotive Engineering International Summer School”, the CA will contract Service provider to ensure the organizing summer school. The procurement rules will be those foreseen by PRAG rules. The contract is Global Price type contract under PRAG 2021.

The price: up to maximum of 5.000,00 EUR. The price represents the maximum budget.

Duration: up to 19.08.2022

The Contractor will receive the Concepts of Modules and subjects according to the specifications book, which must be addressed in the summer school.

The deadline for providing of the service is describe on point no 4.2. Provisional date for contract signature is 28.06.2022.

### Geographical area to be covered

Republic of Moldova

### Target groups

Students and teachers from:

- Technical University of Moldova, Republic of Moldova;

- Technical University Gheorghe Asachi from Iasi, Romania;

- State Agrarian University of Moldova, Republic of Moldova.

## Specific work

| Name of requested services | The quantity | Full technical specification required, Reference standards |
| --- | --- | --- |
| Training services for Project beneficiaries 2SOFT/1.1/11 "Cross-Border Regional Hub of Competences for the Automotive Industry" | Group I (modules 1-6 up to 50 people) Group II (module 7 to 15 people) | Training course: - Course duration: 7 days of 8 hours per day (for Group I) and 2 days of 8 hours each (for Group II); - Number of students in the group: Group I up to 50 (for modules 1-6) and Group II up to 15 (for module 7); - Number of groups: 2; - Implementation period: 7 days (Group I) and 2 days (Group II) in the time period July 01 - July 31, 2022. |

Topics addressed during the training:

| Nr. | Module name | Subjects addressed in each module | Nr. of hours |
| --- | --- | --- | --- |
| 1. | Automotive research and innovation | 1. Current requirements for automobiles and automotive design methods | 2 hours |
|  |  | 2. Automotive research and innovation | 2 hours |
|  |  | 3. Advanced vehicle design | 2 hours |
|  |  | 4. Innovative automotive manufacturing technologies | 2 hours |
|  |  | 5. Interaction of vehicle systems | 3 hours |
|  |  | 6. Car steering systems: the evolution from mechanics to intelligent systems | 3 hours |
|  |  | 7. Moderate discussions on the topics of this module | 2 hours |
| 2. | Automotive control panel systems | 1. Electronic control units for traditional automobiles (MAS & MAC) | 3 hours |
|  |  | 2. The composition and operation of electronic control units for automobiles | 3 hours |
|  |  | 3. Moderate discussions on the topics of this module | 2 hours |
| 3. | Electric and hybrid automotive | 1. Electric and hybrid automotive | 3 hours |
|  |  | 2. Control systems for hybrid and electric automotive | 3 hours |
|  |  | 3. Moderate discussions on the topics of this module | 2 hours |
| 4. | Technical testing and diagnostic systems for automobiles | 1. Modern automotive technical diagnostics systems | 3 hours |
|  |  | 2. Technical testing and diagnostic methods applied in automotive | 3 hours |
|  |  | 3. Moderate discussions on the topics of this module | 2 hours |
| 5. | Organizing trips to auto-service companies and car component manufacturers in the Republic of Moldova | 1. Organizing trips to auto-service companies and car components manufacturers in the Republic of Moldova and video documentation / recording of the trip | 8 hours |
| 6. | Automotive start-ups | 1. Training / training cycle on the issue of start-ups in the field of automotive | 8 hours |
| 7. | Webinars for training, development and administration of online courses on the Moodle platform | 1. Instruction, training in the development and administration of online courses on the Moodle platform | 8 hours |
|  |  | 2. Development and administration of the online course on the Moodle platform to promote the materials within these training courses | 8 hours |

Requirements for the activities required for the conduct of training courses:

a)	Course materials will be developed using practical and innovative work tools (presentations, case studies, examples, etc.);

b)	Providers will develop the curriculum specific to the training course, according to the theme and the full course support, in compliance with the minimum requirements indicated in the Task Book;

c)	Providers will be responsible for contacting the beneficiaries and inviting them to the course, according to the established schedule;

d)	Providers will make available to participants the course support in electronic format, on the online platform Moodle, sent to the e-mail addresses of the beneficiaries;

e)	After completing the training course, the participants will be surveyed, the service provider will prepare a form with questions, which will be sent to the contracting authority to introduce them on the online platform Moodle and make them available to the training beneficiaries.;

f)	The provider will draw up reports to which he will attach the results regarding the daily situation of attendance at the courses (the contracting authority will provide the provider with a model report). The attendance sheet will be drawn up so that the presence of the beneficiaries is checked daily;

g)	The training courses stipulated in module 7 in point 4 “Topics addressed during the training” will be conducted online, using solutions for video conferencing and online meetings (Microsoft Teams or others), which will allow group video calls, will contain interactive chat, where beneficiaries will have the opportunity to ask questions to trainers, will contain options to share the screen, for trainers' presentations;

h)	Providers will be responsible for ensuring the transmission of high quality video / audio signal, so that the material presented by the trainer is visible, the sound is clear to the beneficiaries of the training courses stipulated in module 7 in point 4 “Topics addressed during the training”;

i)	Providers will be responsible for hiring a person who will assist the Trainers in the process of conducting the training courses stipulated in module 7 in point 4 “Topics addressed during the training”, the assistant will supervise the activity of the beneficiaries, will follow and systematize the questions sent of the beneficiaries of the training, will verify the presence of the beneficiaries with the elaboration of the corresponding list, providing specialized support;

j)	The offers will include all the expenses related to the services specified above, specifying the total price and detailing the unit prices.

## Project management

### Responsible body

Contracting Authority: Public Institution "Technical University of Moldova” (TUM)

168, Stefan cel Mare si Sfint Avenue

Chisinau, MD-2004

### Management structure

The Contracting Authority will designate a representative of the institution in charge with the communication and approval of the services offered by the Consultant.

For the day-to-day activity within the Contract, the Contractor will assign an Expert. The daily activity will take place according to the provisions of the Contract and Action Plan agreed with the Contracting Authority and discribed in the Methodology & Organisation.

### Facilities to be provided by the contracting authority and/or other parties

No facilities or equipment will be provided by the Contracting Authority.

# LOGISTICS AND TIMING

## Location

The activities undertaken by the Contractor will take place in Chisinau Municipality.

## Start date & period of implementation

Implementation period:7 days (Group I) and 2 days (Group II) in the time period July 01 - July 31, 2022 Please see Articles 19.1 and 19.2 of the special conditions for the actual start date and period of implementation.

# REQUIREMENTS

## Personnel

Note that civil servants and other staff of the public administration, of the partner country or of international/regional organisations based in the country, shall only be approved to work as experts if well justified. The justification should be submitted with the tender and shall include information on the added value the expert will bring as well as proof that the expert is seconded or on personal leave.

### Key experts

Key experts have a crucial role in implementing the contract. These terms of reference contain the required key experts’ profiles. The tenderer shall submit CVs and statements of exclusivity and availability for the following key experts:

Key expert 1: Team leader

Qualifications and skills:

- University degree proved with diploma, certificate or other similar document;

- Ability to operate with the computer;

- Good communication, organizational skills.

General professional experience:

- At least 3 years of experience in area.

All experts must be independent and free from conflicts of interest in the responsibilities they take on.

### Non-key experts

CVs for non-key experts should not be submitted in the tender but the tenderer will have to demonstrate in their offer that they have access to experts with the required profiles.

The contractor must select and hire other experts as required according to the profiles identified in the organisation & methodology. It must clearly indicate the experts’ profile so that the applicable daily fee rate in the budget breakdown is clear. All experts must be independent and free from conflicts of interest in the responsibilities they take on.

The selection procedures used by the contractor to select these other experts must be transparent, and must be based on pre-defined criteria, including professional qualifications, absence of conflict of interests, language skills and work experience. The findings of the selection panel must be recorded. The selected experts must be subject to approval by the contracting authority before the start of their implementation of tasks.

### Support staff & backstopping

Backstopping and support staff costs must be included in the fee rates.

## Office accommodation

N/A

## Facilities to be provided by the contractor

The contractor must ensure that experts are adequately supported and equipped. In particular it must ensure that there is sufficient administrative, secretarial and interpreting provision to enable experts to concentrate on their primary responsibilities. It must also transfer funds as necessary to support their work under the contract and to ensure that its employees are paid regularly and in a timely fashion.

## Equipment

No equipment is to be purchased on behalf of the contracting authority / partner country as part of this service contract or transferred to the contracting authority / partner country at the end of this contract. Any equipment related to this contract that is to be acquired by the partner country must be purchased by means of a separate supply tender procedure.

## Lump sums

No lump sums are foreseen in this contract.

# REPORTS

## Reporting requirements

Please see Article 26 of the general conditions. There must be a final report, a final invoice and the financial report accompanied by an expenditure verification report at the end of the period of implementation of the tasks. The draft final report must be submitted at least one month before the end of the period of implementation of the tasks. Note that these interim and final reports are additional to any required in Section 4.2 of these terms of reference.

Each report must consist of a narrative section and a financial section. The financial section must contain details of the time inputs of the experts, incidental expenditure and expenditure verification.

## Submission & approval of reports

TWO copies of the reports referred to above must be submitted to the project manager identified in the contract. The reports must be written in English. The project manager is responsible for approving the reports.

* * *