## RMP Supplier
Resource Management Plan, Supplier part
Activity/task
|  |  | Business Analysis | Design | Build | Testing | Training | Documentation | Go Live | Resources TOTAL (by man-hours):
| Category | Number of specialists needed | 1366 | 955 | 6916 | 1779 | 121 | 164 | 942 | 12243
Resources required | Project Manager | 4 | 123 | 112 | 576 | 40 | 3 | 4 | 180 | 1038
| Solution Architect | 3 | 203 | 620 | 1640 | 159 | 0 | 0 | 60 | 2682
| Business Analyst | 7 | 924 | 170 | 930 | 340 | 18 | 112 | 320 | 2814
| Instructor | 1 | 0 | 0 | 0 | 240 | 96 | 16 | 40 | 392
| Software Developer | 12 | 0 | 0 | 3400 | 280 | 0 | 0 | 160 | 3840
| Testing Team Leader | 1 | 0 | 0 | 0 | 320 | 0 | 0 | 80 | 400
| Security Expert | 1 | 78 | 22 | 70 | 160 | 0 | 0 | 62 | 392
| Quality assurance expert | 1 | 38 | 31 | 300 | 240 | 4 | 32 | 40 | 685
Reserve* | Eligible roles - all mentioned above | [8 empty] | 200
* Reserve (Lot I) – 200 man-hours. The reserve may be allocated to the required roles/competencies depending on the change scope (e.g., business analysis, configuration/development, integration/ESB, data migration support, testing/UAT support, documentation).

## RMP Beneficiary
Resource Management Plan, Beneficiary part*
Workload by activity/task
Resources required | Description | Business Analysis | Design | Build | Testing | Training | Documentation | Go Live
Project Manager | Coordination of conducting of the project; preparation and conducting of agreement and approval of overall results of the project. | 100% | 50% | 30% | 30% | 20% | 20% | 50%
Technical Lead | The Technical Lead is a single point responsible for coordination of all development and implementation processes. | 30% | 80% | 50% | 10% | 10% | 20% | 60%
Work Stream Team Lead | The Work Stream Team Lead is a single point responsible for coordination of development and implementation processes for assigned Work Stream. | 80% | 30% | 30% | 60% | 20% | 30% | 50%
Analyst/Consultant | Discussion of the required and existing functionality; discussion of requirements to integration solutions. | 80% | 30% | 20% | 30% | 20% | 40% | 30%
IT specialist | Support of IT infrastructure readiness and system integration activities; participation in data migration, testing processes, and ensuring compliance with internal IT and security requirements. | 20% | 10% | 30% | 70% | 0% | 30% | 80%
Software tester | Execute all the test case and report defects, define severity and priority for each defect. | 0% | 0% | 10% | 100% | 0% | 30% | 60%
System engineer | Consulting on infrastructure. | 20% | 20% | 30% | 20% | 10% | 30% | 80%
* Estimated workload is only an assumption which may widely vary based on the competences of the resources provided, clarity of initial requirements and other factors.